## Event Overview
Event Overview/Event Plan
Event Details
Name of Event:
Event Location:
Event Date:
Event Duration:
Event Coordinator:
Contact Number:
UOW Email:
WHAT IS THE MAIN PURPOSE OF THIS EVENT?
TARGET AUDIENCE FOR THIS EVENT?
EXPECTED ATTENDANCE AT EVENT?
HOW WILL YOU RECEIVE FEEDBACK ABOUT YOUR EVENT FROM PARTICPANTS?

## Planning Procedure
PLANNING PROCEDURE
Items listed below in red are examples for your reference. Please delete all to start with a blank table and add in a planning procedure relevant to your club's event.
| DESCRIPTION | TASK | RESPONSIBILITY | STATUS
December
|  | Seek ideas, research what other clubs and societies do and what needs to be changed | All | complete
|  | Establish the dates and times of the event |  | in progress
|  | Discuss what worked well the previous year and things that the group might to improve on or implement |  | overdue
| Marketing | Decide what marketing you need and the due date for deadlines
| Performers | Seek quotes for Performer
| Catering BBQ | Quote for Catering for BBQ and one other food option.
| Activities | Suppliers prices + availability
| Logo/Design | Draft designs for marketing collateral approved
| Sponsorship | Develop and distribute sponsorship proposal to External Partners
| Venue | Decide and lock in venue - ensuring resrach has been done to fit the best venue to the event
| Establish Facebook Event Pages | Construct Clubs Day Event on Facebook
| Club Wesbite | Construct Club Calendar event on the UniClubs Website for approval via the UniClubs team
| Budget Confirmation | Budget needs to be confirmed as promo of events will need to take place
Janurary
| Website | To go live as soon as approved and any upates need to go on both UniClubs Website and Facebook event
| Contracts | Send all performers their contracts via e-mail, (Individual contracts stating exact times and price)
| Catering | Confirm food options for all events
| Floor Plan | Build floor plans.(If needed)
Deco's + Theming
| Runsheet's | Draft run sheets- This will include volunteer shifts, load in time of suppliers and performance times and other activities that are running.
| Contracts | Signed copies due back from all performers
| Sound | Book in Sound Technician for event or book in equipment to hire
9 weeks
| Invoices | Start collating Invoices/receipts
| Signage | Discuss what types of signage we want
| Risk Assessments | Finalise Risk Assessments
| Schedule App | Send through to UniClubs Team required information to post on UOW App
| Facebook Event posts | Place a schedule together to keep people thinking about the events
| Reminder e-mails | All providers, supplier and performers and Clubs
| Floor Plan | Work on all floor plans including wet-weather ( allocate all stalls)
| Confirm Table order | Establish exact table amount to be communicated to SSD to ensure faculty sessions have enough tables
| Performers | Chase up any performers who have not confirmed and book any last minute performers
6 weeks
| Security | Notify FINAL event times + security involvement
| Facebook Event posts | schedule posts to keep people interested
| Waste Management | ensure there is enough bins for event both recycling and general waste
5 weeks
| Signage | Order signage through sign obsessions or snap printing
| Equipment | Orgainsie and purchase equipment
4 weeks
| Floor Plans | Finialise Floor plans for all events
| Facebook Promotions | Place promotion onto indivdual facebook event pages
| Event Plans | Collate and construct all runsheets maps and floor plans into supplier packs for various stakeholders
3 weeks
| MC Notes | Complete MC communications
| Venue | Contact and confirm venue date and timings
| Event Plans Cont. | Collate and construct all runsheets maps and floor plans into supplier packs for various stakeholders
2 weeks
starting MONTH | Event Plans to be sent out | Send Out final Events plans to suppliers, performers and key stakeholders involved in planning
| MC notes | Create notes for each activity and include info on what I shappening throughout the event
| Final Committee Meeting | Discuss any last minute items that need to be resolved
1 weeks
| Phone Calls | Call all supliers and performers to ensure that everyone is aware of responsibilities
| Brief Assistant | Brief executives/volunteers to ensure appropriate roles and responsibilities are clarified
| Facebook Event | Ensure adequte vamp up is happening in the facebook event
| Loading Equipment | Take equipment to the appropriate places across campus pre event day
0 weeks
Event Day |  | WOO! We can do it!
| Post event evaluations | Post event feedback is given to partcipants/attendees
| Team Debrief | Ensure that all people involved in the planning and execution of the event come together to go over what went well, what can be improved and how to make next years event better.
| Clubs Website | Results and event attendance is updated
| Funding | Receipts are submitted to UniClubs with event title and club written on receipt.
Note on E41: kberry: Send maxine a email 1 week prior

## Runsheet
Event Day Runsheets
KEY CONTACTS
Events Staff
Name | Position/Role | Phone Number | Email
External Contacts
Name | Company | Phone Number | Email
Deliveries Prior to Event Day
Date
Time | Who | What
Task List
Day and Date
9am
10am
12:00pm- 3:00pm
3:00pm
RUNSHEETS
Day and Date | Activity /Time | RESPONSIBILITY
7am
8am
8:30
9:00am
9:30am
10:00am
10:30am
11:00am
11:20am
11:30am
11:40am
12:00pm
12:20pm
12:40pm
1:00pm
1:20pm
1:30pm
1:40pm
2:00pm
2:15pm
2:30pm

## Budget
Event Title, Day and Date
Items listed below in red are examples for your reference. Please delete all to start with a blank table and add in a planning procedure relevant to your club's event.
Activity Expenses | 2013 Budget | 2013 Actual | 2014 Budget | 2014 Actual | 2015 Budget | 2015 Actual | 2016 Budget | 2016 Actual | 2017 Budget exc gst | Purchase orders | 2017 Actuals | Budget Exc GST | Actuals | Comments
Photgrapher/Videographer
Waste | 140 | 140 | 140 | 53 | 140 | 90.66 | 140 | 140 | 140 | 140 | 100 |  |  |  | Southern Cross security | 159.6 | Invoice went through to Steve working with Ella to get it paid
Tables
Power
Crossiants
Club Funding
Bean Bags
Music Performace
Marketing corflute signs |  |  |  |  | 800 | 421.29 | 400 | 460 | 460 |  | 460 |  |  |  | Melanie Stjepanovic | 100 | Uploaded invoice 7/3
estimated cost | [11 empty] | 0
TOTAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | 0
Event Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
Total Invoiced Amount
Note on H13: Kayla Berry: 58.75 for the letter O, glue gun and glue sticks, core flute 43.33 Paint and zip ties + Supplies for signs 21.13 + Aerosol artist
Note on K5: Kayla Berry: emailed 10/11
Note on L5: Kayla Berry: PO Created 19/01/2017
Note on L6: Kayla Berry: Purchased order established 16/1 to FMD need to place the beims request in

## Risk Assessment
EVENT:
Name |  | Date Completed
Club Name & Executive Position |  | Date for Review
ACTIVITY | POTENTIAL RISK | LIKELIHOOD | SEVERITY | RISK PRIORITY | TREATMENT | RESPONSIBLE PERSON | TIMEFRAME
PLANNING (PRE-EVENT)
FINANCIAL
OPERATIONAL (DURING EVENT)
POST EVENT

## Past quotes
BBQ
Venues
Decorations
Performers
Total :
Equipment
Note on C18: kberry: 5 Umbrella
Note on E3: kberry: 400 sausages
Note on F2: kberry: for 36 Vegie Patties
Note on F3: kberry: Per kilo
Note on F4: kberry: Tomato Sauce 4 L
Note on F5: kberry: BBQ Sauce 4 Litre
Note on F7: kberry: 5 KG a bag

## Shopping List
Shopping List | Cost | Amount | QTY
Bunnings |  |  |  | examples have been provided, please delete these before inputting your shopping list
Festoon Lights
Esky
Duct Tape
Szip Ties 2 Bags
Scisors
Tongs x 4
2x Flippers
BBQ Trays x 18
Paper Towels
Cleaners
Office Works
Servo
Kmart
IGA

## Volunteer Managemnet
Volunteer Management
DAY AND DATE | WHO | Time
task/responsibility
Sober Agents

## Promo Plan
Media type | Message | image/visual | date published | comments