## TO COMPLETE - Risk Assessment
EVENT NAME:
Name & Executive Position: |  | Date Completed:
Club Name: |  | Date of Event:
Event Name: |  | Date Last Updated:
UniClubs Assessor: | UniClubs office use only | Date Reviewed: | UniClubs office use only
First Aid Officers [email certificates to pulse-uniclubs@uow.edu.au]
Sober Officers - 1 per 50 attendees
Food Safety Certificates [email certificates to pulse-uniclubs@uow.edu.au]
ACTIVITY | POTENTIAL RISK | LIKELIHOOD | SEVERITY | PRE-MITIGATION RISK PRIORITY | MITIGATION - LESSEN OR REMOVE THE RISK | POST MITIGATION RISK PRIORITY | TREATMENT - ACTIONS TAKEN IF THE RISK OCCURS | RESPONSIBLE PERSON | TIMEFRAME
PLANNING (PRE-EVENT)
FINANCIAL
OPERATIONAL (DURING EVENT)
POST EVENT

## HOW TO COMPLETE - Example Risks
EVENT NAME: Networking Event |  |  |  |  | Below are some risks that could be considered for any event. There are other risks that could occur in each unique event, so your Risk Assessment should include additions to what is below. DO NOT copy and paste, please re-write risks into the 'Risk Assesment' tab and make them relevant to your event and club. Risks highlighted below are non-negotiable risks and must be included in the 'TO COMPLETE' sheet for your event to be approved.
Name & Executive Position | John Smith - Events Coordinator | Date Completed | 1st March 2024
Club Name | Risk Asessments Fan Club | Date of Event: | 22nd March 2024
Expected Attendees | 100 | Date Last Updated: | 8th March 2024
UniClubs Assessor: | Rachel Tidbury - UniClubs Coordinator | Date Reviewed: | 8th March 2024
First Aid Officers - email certificates to UniClubs | John Smith
Sober Officers - 1 per 50 attendees | John Smith | Muhammad Hadi
Food Safety Certified - email certificates to UniClubs | John Smith | Muhammad Hadi | Lisa Chen
ACTIVITY | POTENTIAL RISK | LIKELIHOOD | SEVERITY | PRE-MITIGATION RISK PRIORITY | MITIGATION - LESSEN OR REMOVE THE RISK | POST MITIGATION RISK PRIORITY | TREATMENT - ACTIONS TAKEN IF THE RISK OCCURS | RESPONSIBLE PERSON | TIMEFRAME
PLANNING (PRE-EVENT)
Communication with Attendees | The location, time and other details of the event are miscommunicated to the attendees, resulting In attendees showing late or not at all. | Possible | Insignificant | Low | eg. Ensure date, times and location are present and consistent on all promotion. Send out a reminder email/text to registered attendees the day before the event. | Minimum | eg. Check in registered attendees and contact latecomers to see if they are still attending. | eg. John Smith - Event Organiser | Planning
Weather and Natural Disasters | Wet weather meaning the event can't be outdoors or storms/flooding/winds/etc. leading to the attendees unable to get to/from the event. | Unlikely | Major | Medium | eg. Check weather reports leading up to the event and have a backup space as a wet weather plan. | Low | eg. Cancel, postpone or change location. Notify attendees as soon as possible. | eg. John Smith - Event Organiser | Planning
Transportation - getting to/from the event | The event is not easily accessible via public transport and/or lack of parking |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Communication between club members | Club organisers are not on the same page with the organisation or logistics of the event. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Accessibility | The event is not accessible to people of all abilities (including venue, promotion, communications). |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Before event begins
Venue | The venue has hazards such as tripping, electrical, fire, etc. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Before event begins
FINANCIAL
SSAF Funding | Funding application is not approved or approved for less than requested. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Budgeting | Attendee requests a refund. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Budgeting | Purchases exceed the funding amount approved by UniClubs. |  |  |  | The club must cover the excess funds. |  | [how will you treat the risk?] | [name of executive] | Planning
Budgeting | Receipt isn't submitted by the 3 month period |  |  |  | The club must cover the excess funds. |  | [how will you treat the risk?] | [name of executive] | Planning
Sponsorships | The sponsors do not uphold their end of the agreement (eg. they don't pay the club). |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Suppliers and Vendors | Suppliers pulling out of the event. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Suppliers and Vendors | Invoices are not paid in time. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
Suppliers and Vendors | Breakage of venue/supplier property or hired equipment, resulting in a damage fee. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Planning
OPERATIONAL (DURING EVENT)
Participating in the event | Minor Injury. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | Major Injury. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | Sexual/Physical/Verbal/Emotional Harrassment. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | Bullying or Cyberbullying occurs. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | An attendee has COVID or other transmittable diseases. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | Patrons intoxicated from drugs or alcohol. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | Drink spiking. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | An attendee is feeling uncomfortable, upset or overwhelmed. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Serving Food | Attendees have allergies or dietary requirements. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Serving Food | The food is undercooked or not prepared safely. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Venue | Venue reaches capacity. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Venue | Evacuation occurs. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Vendor Arrival | Vendor arrive late or cancels last minute. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Participating in the event | Criminal activity such as theft. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Transportation | There is lack of public transport or parking for attendees to get to and from the location. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Security | The venue does not have security. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
Waste Management | There are no bins provided or the bins provided do not have the capacity to hold the waste from the event. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Duration of event
POST EVENT
Feedback | There is no way for attendees to give the club feedback, resulting in lack of improvement for the next event. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Post event
Debrief | The event organisers do not discuss how the event went, resulting in the next event having no improvements. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Post event
Incident Reports | Incidents are not reported. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Post event
COVID/other transmittable diseases | The organisers discover an attendees has contracted a transmittable disease from the event. |  |  |  | [how will you mitigate this risk?] |  | [how will you treat the risk?] | [name of executive] | Post event

## Key Descriptors
LIKELIHOOD
Level | Descriptor | Example detail description | RISK PRIORITY
A | Rare | May occur only in exceptional circumstances | Likelihood | Severity
B | Unlikely | Could occur at some time |  | 1 - Insignificant | 2 - Minor | 3 - Moderate | 4 - Major | 5 - Catastrophic
C | Possible | Might occur at some time | A - Rare | Minimum | Minimum | Low | Low | Medium
D | Likely | Will probably occur in most circumstances | B - Unlikely | Minimum | Low | Low | Medium | High
E | Almost certain | Is expected to occur in most circumstances | C - Possible | Low | Low | Medium | High | High
SEVERITY |  |  | D - Likely | Medium | Medium | Medium | High | Extreme
Level | Descriptor | Example detail description | E - Almost Certain | Medium | Medium | High | Extreme | Extreme
A | Insignificant | No injuries; low financial loss
B | Minor | First aid treatment; on-site release immediately contained; medium financial loss
C | Moderate | Medical treatment required; on-site release contained with outside assistance; high financial loss
D | Major | Extensive injuries; loss of production capability; off-site release with no detrimental effects; major financial loss
E | Catastrophic | Death; toxic release off-site with detrimental effect; huge financial loss

## Version Control - office use
PROCEDURE: UNICLUBS RISK ASSESSMENT TEMPLATE
Version | Last Edited | Last Editor
1 | 2024-09-18 | Rachel T.
CHANGES TRACKER
Date of Change | Changes made / by whom | Version No.
2024-09-18 | New example risks, certificate submissions, Pre and Post Mitigation priorities and version control table added / Rachel T. | 1
2024-10-09 | Non-negotiable risks added to Example Risks / Rachel T. | 1.1
2025-07-24 | Receipt deadlines added to budgeting risks / AM | 1.2